## Sheet1
On going chart
Key
Task | Who carried it out | Date completed | Progress | Expected duration (Days) | 0 | = completed / to be completed in in the same day
Project Idea (Proposal) | All members | 2017-01-25 | Done | 8
Risk Assessment | Reiss | 2017-02-17 | Done | 5
Mind Map (Porject Management) | Ikechukwu | 2017-02-19 | Done | 5
Stortry board for webiste | Christopher Butt and Nathan Zengamabu | 2017-02-02 | Done | 10
Reasruch on compeditors (Apple Music and Sporiflity) | Christopher Butt, Tom Quinn and Mohammed Khan | 2017-02-12 | Done | 0
First go at website (Basic) | Christopher Butt | 2017-02-12 | Done | 14
Gantt Chat (That does not change) | Christopher Butt | 2017-02-26 | Done | 0
Project management (Gantt Chart, etc.) | Christopher Butt and Nathan Zengamabu | 2017-02-26 | Done | 1
Work-break down strecture | Nathan Zengamabu | 2017-02-27 | Done | 4
Meeting up to work on webiste (Chris Butt and Nathan) | Christopher Butt and Nathan Zengamabu | 2017-03-03 | Done | 1
Meeting up to work on webiste (Chris Butt and Nathan) | Christopher Butt and Nathan Zengamabu | 2017-03-04 | Done | 0
Oher compeditors reseach (Deezer) | Nathan Zengamabu | 2017-03-04 | Done | 2
Business Side (Artists get paid) | Tom Quinn | 2017-03-06 | Done | 0
Business Side (Revenue Steam) | Tom Quinn | 2017-03-06 | Done | 2
Logo created | Tom Quinn | 2017-03-08 | Done | 6
Privacy | Tom Quinn | 2017-03-14 | Done | 1
Meeting to look at progress Wednesday (13.00 to 14.00) | All members | 2017-03-15 | Done | 1
Adding a serach bar | Nathan Zengamabu | 2017-03-16 | Done | 3
Social Side (First part) | Christopher Butt | 2017-03-19 | Done | 0
Ethical side | Christopher Butt | 2017-03-19 | Done | 1
Website updated (Addnew a different colour theme) | Nathan Zengamabu and Christopher Butt | 2017-03-20 | Done | 0
Layout change of website | Nathan Zengamabu | 2017-03-20 | Done | 2
Meeting to look at progress Firday (8.00 to 10.00) | All members | 2017-03-22 | Done | 5
Adding button to make text longer | Christopher Butt and Nathan Zengamabu | 2017-03-27 | Done | 2
Creating a Gitbut to share code | Nathan Zengamabu | 2017-03-29 | Done | 3
Meeting to go over project (Creating video) | Christopher Butt and Nathan Zengamabu | 2017-04-01 | On going | 0
Feedback Questionnair (Website) | Christopher Butt | 2107-04-01 | Done | 0